## Basic Manual Gantt Chart (hidden)
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date (hidden)
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Experiments and Causal Inference Timeline
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43029 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Progress Report | 2017-10-21 | 2017-10-31 | 5 | 0.5 | 9.5 | 5%
Find Additional Profile Volunteers | 2017-10-25 | 2017-11-02 | 8 | 0 | 8 | 0%
Write grant proposal | 2017-10-25 | 2017-11-02 | 8 | 0 | 8 | 0%
Run Pilot | 2017-10-27 | 2017-11-04 | 8 | 0 | 8 | 0%
Review Pilot Results | 2017-11-03 | 2017-11-07 | 4 | 0 | 4 | 0%
Collect Data | 2017-11-10 | 2017-11-17 | 7 | 0 | 7 | 0%
Collect Data | 2017-11-17 | 2017-11-23 | 6 | 0 | 6 | 0%
Review Data | 2017-11-22 | 2017-12-02 | 10 | 0 | 10 | 0%
Problem Set 4 | 2017-11-16 | 2017-11-22 | 6 | 0 | 6 | 0%
Thanksgiving | 2017-11-20 | 2017-11-27 | 7 | 7 | 0 | 100%
Team Feed Back | 2017-11-29 | 2017-12-05 | 6 | 0 | 6 | 0%
Collect Data Round II | 2017-12-01 | 2017-12-06 | 5 | 0 | 5 | 0%
Collect Data Round II | 2017-12-02 | 2017-12-07 | 5 | 0 | 5 | 0%
Review Data Round II | 2017-12-05 | 2017-12-08 | 3 | 0 | 3 | 0%
Problem Set 5 | 2017-12-06 | 2017-12-13 | 7 | 0 | 7 | 0%
Final Project Due | 2017-11-29 | 2017-12-13 | 14 | 0 | 14 | 0%
Research supporting studies | 2017-10-21 | 2017-11-30 | 40 | 4 | 36 | 10%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Sheet1
Date
8 | Incomplete Control of D | FE 5 | G&G 2005, RMKB: 1. intro, 2. threats 3. types, 4. two-groups, 5. blocks | PS 3 | 2017-10-18
Fall Break |  |  |  |  | 2017-10-25
9 | Spillover | FE 8 and lyft and uber | Miguel and Kremer; Blake and Cohey 2, 3 | Progress Report | 2017-11-01
10 | Problems and Building Paradigm | FE 11.3 | DiNardo and Pischke, Simonsohn | – | 2017-11-08
11 | Causality from Observation? | MM 3.1, 4.1, 5.1 | Incinerators, Washington, Dee (O): Lalive, Rubin, Section 3 | PS 4 | 2017-11-22
12 | Attrition, Mediation? | FE 7, 10 | Alcott and Rogers | Peer Eval 1 | 2017-11-29
13 | Creative Experiments | FE 12, (O): FE 13 | Sherman, Hughes
14 | Final Thoughts |  | Freedman | PS 5 | 2017-12-06
15 | – | Retracted LaCour, (tl;dr), | Broockamn Irregularities | Final Paper, Peer Eval 2 | 2017-12-13